ClinicDesk — Sprint Plan

Based on Vision Document v1.0  |  09 Jun 2026  |  11 Sprints  |  83 User Stories

Methodology: Agile Scrum  |  Sprint Duration: 2 Weeks

# Sprint Summary

| Sprint | Name | Sprint Goal | Stories | Points |
| --- | --- | --- | --- | --- |
| Sprint 1 | Foundation & Auth | Secure login, role management — the system is accessible only to the right people. | 7 | 23 |
| Sprint 2 | Patient Records | Staff can register, search, and manage complete patient records. | 6 | 22 |
| Sprint 3 | Appointment Scheduling | Full appointment lifecycle — booking to check-in — with conflict prevention. | 8 | 31 |
| Sprint 4 | Clinical Documentation | Doctors can record, update, and finalise examination notes per visit. | 5 | 21 |
| Sprint 5 | Prescription Management | Doctors can write, manage, and export prescriptions linked to visits. | 4 | 17 |
| Sprint 6 | Billing & Invoicing | Receptionists can generate invoices, record payments, and configure pricing. | 6 | 26 |
| Sprint 7 | Patient Portal | Patients can self-register, book/cancel appointments, and view their records. | 12 | 36 |
| Sprint 8 | Notifications | Automated reminders and in-app alerts keep patients and staff informed. | 5 | 19 |
| Sprint 9 | Dashboard & Analytics | Admins and doctors have a live operational overview and key clinical insights. | 7 | 24 |
| Sprint 10 | Reports & Export | Admins can generate, filter, and export business and clinical reports. | 8 | 30 |
| Sprint 11 | Localisation, A11y & Polish | Full Arabic/English bilingual support, responsive layout, accessibility, and remaining stories. | 10 | 43 |

# Detailed Sprint Backlog

Sprint 1: Foundation & Auth   (7 stories · 23 pts)

Goal: Secure login, role management — the system is accessible only to the right people.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-X01 | Log in with username and password | All Roles | High | 5 |
| US-X03 | Reset password via email verification | All Roles | High | 3 |
| US-X04 | All data transmitted over HTTPS/TLS | All Roles | High | 3 |
| US-X02 | Session expires after inactivity | All Roles | High | 2 |
| US-A01 | Create new staff accounts (doctor, receptionist) | Admin | High | 5 |
| US-A02 | Assign or change a staff member's role | Admin | High | 3 |
| US-A03 | Activate or deactivate staff accounts | Admin | High | 2 |

Sprint 2: Patient Records   (6 stories · 22 pts)

Goal: Staff can register, search, and manage complete patient records.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-R01 | Register new patients with full personal details | Receptionist | High | 5 |
| US-R02 | Edit existing patient records | Receptionist | High | 3 |
| US-R03 | Search patients by name, ID, phone, or DOB | Receptionist | High | 5 |
| US-R04 | View patient's linked visits, prescriptions & invoices | Receptionist | High | 3 |
| US-D04 | Search and view a patient's complete medical history | Doctor | High | 3 |
| US-D05 | See chronological list of all previous visits | Doctor | High | 3 |

Sprint 3: Appointment Scheduling   (8 stories · 31 pts)

Goal: Full appointment lifecycle — booking to check-in — with conflict prevention.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-R06 | Book appointment for a patient (doctor, date, slot) | Receptionist | High | 8 |
| US-R07 | System prevents double-booking a doctor | Receptionist | High | 5 |
| US-R08 | Reschedule an appointment with reason log | Receptionist | High | 3 |
| US-R09 | Cancel an appointment with reason log | Receptionist | High | 3 |
| US-R10 | View daily and weekly doctor schedule | Receptionist | High | 5 |
| US-R11 | Check a patient in on arrival (→ Checked-In) | Receptionist | High | 3 |
| US-D01 | View my daily appointment schedule | Doctor | High | 2 |
| US-D02 | View my weekly appointment schedule | Doctor | High | 2 |

Sprint 4: Clinical Documentation   (5 stories · 21 pts)

Goal: Doctors can record, update, and finalise examination notes per visit.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-D06 | Record structured examination note per visit (ICD) | Doctor | High | 8 |
| US-D08 | Update examination record while appointment is open | Doctor | High | 3 |
| US-D09 | Mark appointment as completed (locks record) | Doctor | High | 3 |
| US-D07 | Attach scanned lab reports to a visit | Doctor | Medium | 5 |
| US-D03 | See patient's upcoming/past appointments from profile | Doctor | High | 2 |

Sprint 5: Prescription Management   (4 stories · 17 pts)

Goal: Doctors can write, manage, and export prescriptions linked to visits.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-D10 | Create prescription linked to a specific visit | Doctor | High | 8 |
| US-D11 | Add multiple medicines to a single prescription | Doctor | High | 3 |
| US-D12 | Print / export prescription as PDF | Doctor | Medium | 3 |
| US-D13 | View patient's full prescription history | Doctor | High | 3 |

Sprint 6: Billing & Invoicing   (6 stories · 26 pts)

Goal: Receptionists can generate invoices, record payments, and configure pricing.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-R12 | Generate invoice per visit based on services/pricing | Receptionist | High | 8 |
| US-R13 | Record full or partial payment with payment method | Receptionist | High | 5 |
| US-R14 | View payment status of any invoice | Receptionist | High | 3 |
| US-R15 | View and reprint a past invoice | Receptionist | Medium | 2 |
| US-A05 | Configure clinic services and their prices | Admin | Medium | 5 |
| US-A06 | Configure clinic working hours | Admin | Medium | 3 |

Sprint 7: Patient Portal   (12 stories · 36 pts)

Goal: Patients can self-register, book/cancel appointments, and view their records.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-P01 | Register a new patient account | Patient | High | 5 |
| US-P02 | Log in securely to the patient portal | Patient | High | 3 |
| US-P04 | Manage and update own profile | Patient | Medium | 2 |
| US-P05 | Book appointment by selecting doctor, date, slot | Patient | High | 8 |
| US-P06 | Cancel an appointment online | Patient | High | 3 |
| US-P07 | View all upcoming appointments | Patient | High | 2 |
| US-P09 | View full visit history | Patient | Medium | 3 |
| US-P10 | Access prescriptions issued to me | Patient | Medium | 3 |
| US-P11 | Print / export my prescription as PDF | Patient | Medium | 2 |
| US-G01 | Browse clinic info and services without an account | Guest | High | 2 |
| US-G02 | View doctor profiles and specialisations | Guest | High | 2 |
| US-G03 | Be prompted to register when attempting to book | Guest | High | 1 |

Sprint 8: Notifications   (5 stories · 19 pts)

Goal: Automated reminders and in-app alerts keep patients and staff informed.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-P08 | Receive automated appointment reminders (email/SMS) | Patient | Medium | 5 |
| US-P12 | Receive notification when invoice is generated | Patient | Medium | 3 |
| US-X08 | In-app notifications for appointments & check-ins | Staff | Medium | 5 |
| US-X09 | Email notifications with automatic retry | All Roles | Medium | 3 |
| US-A07 | Configure notification channels and credentials | Admin | Medium | 3 |

Sprint 9: Dashboard & Analytics   (7 stories · 24 pts)

Goal: Admins and doctors have a live operational overview and key clinical insights.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-A09 | View system-wide dashboard (today's appointments) | Admin | Medium | 5 |
| US-A10 | View monthly revenue summary with trend chart | Admin | Medium | 5 |
| US-A11 | See top 5–10 most common diagnoses | Admin | Medium | 3 |
| US-A12 | See new-vs-returning patient ratio | Admin | Medium | 3 |
| US-A13 | View upcoming appointments for next 7 days | Admin | Medium | 2 |
| US-D14 | View dashboard with today's appointments (doctor) | Doctor | Medium | 3 |
| US-D15 | See most common diagnoses across my patients | Doctor | Medium | 3 |

Sprint 10: Reports & Export   (8 stories · 30 pts)

Goal: Admins can generate, filter, and export business and clinical reports.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-A14 | Generate patient report (totals, new regs, demographics) | Admin | Medium | 5 |
| US-A15 | Generate appointment report by doctor/day/cancellation | Admin | Medium | 5 |
| US-A16 | Generate billing report (revenue, balances, methods) | Admin | Medium | 5 |
| US-A17 | Generate disease/diagnosis report by date range | Admin | Medium | 3 |
| US-A18 | Export any report as PDF or Excel | Admin | Medium | 5 |
| US-A19 | View all patient records (oversight) | Admin | High | 2 |
| US-A20 | View all invoices and their statuses | Admin | High | 2 |
| US-A21 | View audit logs of sensitive system actions | Admin | High | 3 |

Sprint 11: Localisation, A11y & Polish   (10 stories · 43 pts)

Goal: Full Arabic/English bilingual support, responsive layout, accessibility, and remaining stories.

| ID | User Story | Role | Priority | Pts |
| --- | --- | --- | --- | --- |
| US-X05 | Switch UI between Arabic (RTL) and English (LTR) | All Roles | Medium | 13 |
| US-X06 | Fully functional on desktop, tablet, and mobile | All Roles | High | 8 |
| US-X07 | Meet WCAG 2.1 AA accessibility standards | All Roles | Medium | 5 |
| US-G04 | Switch language as a guest browsing the site | Guest | Medium | 1 |
| US-A08 | Enable/disable the patient self-service portal | Admin | Low | 2 |
| US-A04 | Reset a staff member's password | Admin | Medium | 2 |
| US-P13 | View past invoices related to my visits | Patient | Medium | 2 |
| US-R05 | Deactivate or archive a patient record | Receptionist | Low | 2 |
| US-X10 | Core pages load in under 2 seconds | All Roles | High | 5 |
| US-X11 | System available 99.5% during clinic hours | All Roles | High | 3 |

# Business Alignment

Each sprint is anchored to a documented business pain point from Section 2 of the Vision Document:

| Business Pain Point | Addressed In | Key Stories |
| --- | --- | --- |
| Manual/paper records → loss & illegibility | Sprints 2, 4 | US-R01–05, US-D04–09 |
| No unified scheduling → double-bookings | Sprint 3 | US-R06–11, US-D01–02 |
| Disconnected billing → errors & missed revenue | Sprint 6 | US-R12–15, US-A05–06 |
| No patient portal → heavy front-desk load | Sprint 7 | US-P01–13, US-G01–04 |
| Language barrier for Arabic speakers | Sprint 11 | US-X05, all role language stories |
| No analytics → blind clinic owners | Sprints 9, 10 | US-A09–21, US-D14–15 |

Important Note on Business Validation

The Vision Document (v1.0, draft) has not yet been validated with real clinic users. The stories reflect assumed business needs based on a well-reasoned problem statement. Priorities and acceptance criteria should be reviewed with actual receptionists, doctors, and clinic owners before development begins.

ClinicDesk Sprint Plan  |  Generated from Vision Document v1.0  |  Confidential — Internal Use Only